## Sheet1
EWSNetwork
Program Task Form
GP = group program EC = email campaign K = kiosk campaign HF = health fair
PWP = personal wellness profile AGP = awareness group program (team challenge)
ANY Handouts, Presentations, Recipes, Walkaround intiatives, theme days, etc… to be sent to Head Office for approval 3 days to 1 week in advance [at least]
Company
Program
Start Date
Start Time(s)
Program Length
4 weeks before
room booked
needed AV equipement booked
instructor contacted
instructor booked
instructor bio
instructor 5 tips
inform consultants of program
poster created
email campaign created
program rules, instructions created
K - trifold gathered
K - materials gathered (BP cuff, scale, fish bowl, handouts etc…)
PWP - posters created
PWP - posters printed
PWP - pay stubs created
PWP - pay stubs printed
PWP - kits mailed to contact person
HF - schedule drafted
HF - rooms booked
HF - strategic affiliates contacted
HF - strategic affiliates booked into slots
HF - strategic affiliates needed equip booked
HF - strategic affiliates bios, logos, and outlines requested
3 weeks before
posters printed
posters posted
poster emailed to WC to post
GP - email #1 to staff (it's coming)
AGP/challenge - email #1 to staff [it's coming]
EC - gathered
K - trifold printed
K - handouts printed
PWP - posters posted
HF - email #1 to staff (it's coming)
HF - strat affiliates follow up on missing info
HF - finalize schedule of events
HF - create sign up sheets
HF - create poster
2 weeks before
confirm instructor / speaker
sign up sheet created
sign up sheet posted
GP - email #2 - (sign ups, details, poster attached)
AGP/challenge (teams signed up, poster attached, details in email)
EC - email #1 - it's coming
K- email #1 - it's coming
PWP - email #1 - it's coming
HF - email #2 - (schedule and sign ups)
HF - email sign up sheets, schedule, and poster to WC to post
HF - post posters
HF - post sign up sheets
HF - confirm strategic affiliates - time, event, address of site
3 days to 1 week before
GP - email final reminder to participants
GP - sign up sheet emailed to faciliitator
AGP/Challenge - email final reminder re: teams or other details
EC - dates on calendar (day per week/month)
HF - email #3 - (final reminder about sign ups)
ANY Handouts, Presentations, Recipes, Walkaround intiatives, theme days, etc… to be sent to Head Office for approval
day of event
GP - final reminder to all staff
AGP/Challenge - final reminder to all staff to launch program
EC - email sent to staff
PWP - email #2 - reminder site is live
K - set up on-site and reminder email on location, details
last 2 days of campaign
PWP - final reminder about end date
2-3 days following
GP - evaluation emailed to participants
GP - gather sign up sheets
HF - thank you notes done
HF - thank you notes mailed